## Slide 1: CCI Connect Site
Jamel Douglas
Zachary Bresler, Brandon Rodgers

## Slide 2: Focus/Goal
Increase traffic to the connect.cci.fsu.edu website, promote the site
  100 views on home page
  30 views on blog page
  30 views on videos page
Create resources for students. Blog posts, informational posts, videos.
  Curate 3 blog posts (No Blogging FSU group this semester)
  Contact other groups, post their content on the site
Keep events updated on the website

## Slide 3: Base Metrics (Last 90 Days)
Mar 12, 2021 – June 9, 2021
84 unique users
  81 new users

## Slide 4: Base Metrics (Last 90 Days)
Homepage had 100 views
Resource page had 9 views
  Link page had 18 views
  Video page had 37 views
  Program page had 5 views
Blog page had 36 views

## Slide 5: Progress
Received Metrics
Quantified goals

## Slide 6: What’s Next
Create a plan to promote the site. Execute plan.
Create blog posting schedule
Get content for site
  Blog posts from group members
  Videos from CCI Video and STEM HS Video groups.
  General content from Get Involved group

## Slide 7: Roles
Jamel D
  Site promotion plan
  Create blog posting schedule
  Write a blog post.
  Contact the Get Involved group, ask to post content on site.
Brandon R
  Write a blog post.
  Contact the CCI Video group, ask to post content on site.
Zachary B
  Write a blog post.
  Contact the STEM HS Video group, ask to post content on site.

## Slide 8: 3-Week Plan
Week 1
  Site promotion plan
  Blog posting schedule
Week 2
  Connect with other groups, see where they are at in terms of completion
  1st blog post
Week 3
  2nd blog post
  Start posting other groups content.

## Slide 9: Issues
I didn’t realize that there is no Blogging FSU group this semester, so our group will be filling in that content gap.

## Slide 10: Progress Rating
1 – Behind Schedule